# Education, health and care plan 20-week process

## Weeks 1 to 6

- Referral made

- Referral stored securely and entered on tracker

- SENMAS checklist

- Request for background information sent

- Background information returned

- Information collated

- Circulation of papers

- Education panel – decision made to assess or not

## Weeks 7 to 16

- Request for advice if assessing

- Children or young person’s and parent’s views obtained in a meeting

- Agencies work on advice

- Advice submitted and collated

- Advice – follow up, chasing, etc

- Education Panel – decision to issue EHCP or not

### If decision is made to issue EHCP:

- Draft EHCP written

- Draft sent to parents and professionals

- Amendments made to draft EHCP if needed

## Weeks 17 to 20

- If required, Joint or Complex panel

- Final EHCP issued

- Place/services commissioned